Quality Standards in Project Implementation

Definitions:

Project context

PCM

Project parameters

Implementation

Quality Standards

Content Process

Exchange Process

Interface Process

Table of contents:

1    Limits to Quality Standards and reasons to re-plan and re-define

widely applicable approximation

2    Latent processes in implementation and influence on Quality Standards

a short-cut for quick lessons

3    Latent processes and biases in Logframe – practices

4    Common parameter forms for sector policies

specific to the project, first suggestion for further detail

5    Transferability of latent processes and project parameters

6    Overview of parameters shaping processes and Quality Standards

7    Example of a parameter and its influence on variable Quality Standards

example to demonstrate the level of detail possible

8    Necessary analytical steps for formulation, management, evaluation

9    Levels of data in project cycles

10    Realistic first analytical steps

11    Example parameter list and generally decisive latent processes

widely applicable approximation

1.   Why Quality Standards evolve during implementation

| EU Quality Standard |  | Causes of change for a Standard | Insights from a workshop on latent processes with the project participants |
| --- | --- | --- | --- |
| 8.1 15.4 | Institutional arrangements and capacity | analysis always insufficient as negotiated, behavioural and cognitive components of institutions are not clear, management and responsibilities must bring new issues | improvements in understanding, new factors, esp. on ownership |
| 3.4 | Key stakeholders’ institutional structures, capacity and governance | analysis always insufficient, project implementation brings out issues, such as extent of networks and trust | realign contributions and roles according to project progress |
| 3.3, 3.2 | Stakeholder interests and conflicts | participants’ perceptions of contextual issues, new coordination opportunities and joint efforts evolve | opportunity for participants to consider their conflicts |
| 2.3 | Linkages to policy, programmes and projects | development effectiveness debate, DAC realignment, sector spillover assumptions | scoping for new issues, esp. capacity building linkages |
| 5.3 | Implementation strategies | strategies are incomplete, aid operation policy modifications | suggestions how to address new issues |
| 5.2 | Complementarities with other donors | changes in donor coordination and priorities, new harmonization opportunities appear | realigning project components and procedures |
| 6.1 | Demonstrated contribution to long term outcome | general economic, social and political instability | only early warnings on future issues |

Quality Standards in the framework which address changes during implementation:

14.4	operational plans reviewed and updated with lessons learned from experience on the ground

8.3 	support the ability of managers respond to changing circumstances on the ground

6.5	design allows for necessary changes to operational plans

2. Latent Processes (ideal interactions) shaping implementation

instrumental

technical core

foreign

sociocultural ends

local

sociocultural ends

foreigner´s image

of local ends

local´s image

of foreign ends

Exchanges about

ends and core

Content Process

Its influence increases the less

participants can express how

they find that others misjudge

the technical knowledge

The process reflects

contextual factors from

professional socialisation:

education, organisational culture,

biases of professions, heuristic habits

| Key parameters in PCM local/foreign output, performance criteria | often shape  | 8.1 Institutional arrangements and capacity building 3.4 Key stakeholders’ institutional structures 3.3 stakeholders’ interests and conflicts |
| --- | --- | --- |

Exchange Process

Endo-social format: participants can not shape the 		     Reflects:

passage with knowledge, know-how is deficient	   social history, national

Exo-social format: participants shape the passage,	     interest, globalization,

thereby affecting relations but reduce intrinsic	     local social identity,

quality of knowledge, artefacts, design, data	       each format a rigid Habitus

| Key parameters: meetings and agendas, accessory data | often shape  | 5.2 Complementarities with other donors 8.1 Institutional arrangements and capacity building 5.3 Implementation strategies |
| --- | --- | --- |

Interface Process

developee  foreign                    local      developer

image      rhetoric                  rhetoric     image

Interface

Stabilizes misunderstandings, esp.

expressed and hidden roles

Reflects the average communication skill

level, how participants express their

roles, example: images are expressed

(in rhetoric) but do not affect another

| Key parameters: budgeting, reporting, non-essential aspects | often shape  | 3.3 Stakeholders’ interests and conflicts 3.2 Stakeholders’ consultation and concerns 2.3 Linkages to programmes and policy |
| --- | --- | --- |

3.   Latent processes causing biases in Logframe practices

| Evidence: Vertical LF-habits | Cause:  Exchange Process | EU - PCM intent: Quality Standard |
| --- | --- | --- |

elevated purposes and		driven by doubts on	5.2 Complementarity with

outputs, often with		local / global relations’	  programmes/projects incl.

increase of assumptions,		future  			  other donors assessed

“jamming” for legitimacy		local interest formation	8.1 Management

lack of specificity,			either strong, hidden	responsibilities build on and

mechanical links between		and unsound (exo case)    promote institut. capacity

input and outputs,			or weak and isolated        5.3 Implement. strategies

“lock-frames”			(endo case) 			    and further formulation

stakeholders maintain		encounters reinstated	    work analysed

different intervention	  Content Process    .

logics				experts anticipate the    15.4Institut. strengthening

Horizontal LF-logic    	need to claim that		     and capacity building,

excessive number of		ends were universal	     skills transferred

indicators, too many		applications of skills        3.4 Key stakeholders’

national measures			are not additive		     institutional structures

capacity building is			results isolated,		     and capacity assessed

stated as project output		available local know-	3.3 Conflicts between

excessive assumptions		how not recognized	     stakeholders explicitly

about the orientation of		accusations of deceit	     identified and analysed

institutional reforms		or of incapacity of          3.2 Stakeholder identifica.,

stakeholders keep and hide	professionalism		     consultations and

different assumptions		stakeholders are more	     concerns analysed

about indicators			professional groups	2.3 Linkages with policy,

stated assumptions are not	than socio-economic	 programme and projects,

independent of a project	ones			          supportive of PG initiatives

quantitative proxy indicators  Interface Process  .

intended to compensate		foreign knowledge	          9.4 Target groups have the

vertical changes			remains linked to		     means and information

incentives for goal			experts’ traits		     to voice their concerns

attainment hide control		in unacknowledged and	8.3  Review, planning,

targets reduce learning		asymmetric contexts 	     budgeting fit with local

and building capacity		strategic revealing		     systems, respond to

esp. for activities		of information is		     lessons learned and

data fetishism substitutes	dangerous			     changing circumstances

for judgement			roles evolve dynamically	9.3  Responsibilities for

non-existent baselines		with successive		    reporting and using info.

Logframes rarely updated	individuals			    build on existing systems

4. Parameter forms for the implementation of sector policy

Example from a public infrastructure project

Common

Parameter	    Form	 	 Possible Sector Policy Element

task structuration	    horizontal       Can focus industrial sector organizations, ex: trade and craft

-		     associations, clusters, types of firms or economic orgs.

vertical	  When socio-professional groups are representative for

stakeholders, respective norms or conflicts are involved.

local / foreign task	     parallel         Can challenge professional biases and paradigms, educational

division		          -		   structures, industrial relations, regional economic alliances.

intermittent    Task definitions link economic spheres for infrastructure;

also technology transfer and technology cooperation projects.

knowledge output,	     function 	  Defining functions highlights networks or vertical economic

technology	          -		    linkages, knowledge management, educational structures.

object	  Embodied knowledge can align know-how from different org.

budgeting,	   aggregated 	  Shapes risks for stakeholders and social or group identities,

inventories	           -   	    local governance, assists strategic groups and regime types.

specific	  HRM, reduces ambiguities of roles, more programme links.

performance 	 discretionary 	  Better attribution to groups and know-how, HRM, rational

indicators	          -   	   choice limits, variable participation, ex: trade promotion.

public	 Internal negotiation in orgs. transmitted to stakeholders.

decisions			     vertical	      Stakes and contributions fixed and authority externalised.

-		     Nests and nodes can realign stakes and differentiate learning

nested	     from monitoring, sociocultural groups or casts relate further.

meetings and	     separate, fixed  Change in subject/object relations, realign social identities

agendas			          -			   with policy carriers, knowledge embeddedness deepened.

intermittent	 Allows ambiguity when roles and rhetoric interact, links with

other institutions and OD, ex: mainstreaming social policies.

role conflict	    passively 	Endo case:follows social history, when authenticity essential,

tolerated -	  ex: public policy. Exo case: where formalism is a precondition.

acknowledged	 Endo case: focus on adaptation, such as in economic planning.

Exo case:forces project out of social history,new institutions.

evaluation		        negotiated	 Improves efforts to translate, group autonomy, encourages

-    	  change agents and leadership, supports aid history analysis.

fixed	      Project trails local politics or brokers, social investment pilots.

official reporting,	    integrated	Better attribution in uncertainty or competitiveness, ex: FDI.

documentation	          -		Reduces rhetoric scale of role claims, ex: unlock expertise in

separate	  complex planning; only in endo case: individuals disown group.

language,			      create 		 Supports know-how, efforts to translate more relevant than

terminology		  dictionary  -	   content, equivalence always in progress, knowledge corpora.

all vernacular	 Metaphors are censured so that no label is used,	ex: health.

employment,		  show all TOR	 Supports profiles, increases defensiveness, fosters explicit

remuneration		  	    -			   knowledge exchanges, endo case: increases individual failure.

hide terms	 Creates distance, role suspicion, encourages folk theorizing.

accessory data,		    extensive 	 Exo case: shifts otherness (cultural marker) to new objects in

calculations			    -			  social history, supports local knowledge; endo case: diffuse.

little		 Reveals sector specific biases in professions, ex: environment.

non-essential aspects:	       group 		 Exo case:supports social identity, binds dominant stakeholder.

hours, travel, tools,  		     -		 Endo case: individuals pledge social identity and norms.

office, etc.			     individual	 Reduces or reinforces group identity when local or foreign

images are referred to, specific for a sector, also in HRM.

5.   Transferability of project parameters

Country X		      Project A  	    	           Country Y		   Project B

policies	 	-vertical tasks		      	    policies	      -

stakeholders  	-output is function    		 stakeholders     -  different

history		-codify know-how			    history	            parameters

-specific budgets					      -

Sector		-nested decisions			   Sector	      -

market		-admit role conflict		   market	      - different order

org. field	  	-groups to objects	  	  	 org. field	          of parameters

trust		-formal roles			     trust	      -

norms		-individual authority	    	     norms	      -

associations 	-integrated reports 	  	associations	      -

professions	-fixed meetings	 		 professions	      - different form

communities	-separate groups    		communities	          of parameters

-more line positions				      -

aid agency 	-public milestones			 aid agency 	      -

experience	-public housekeeping    		experience	      -

recruitment	-fixed terminology  	         recruitment        -

aspiration	-TORs hidden	    		 aspiration	      -

emotion		-extensive data           		  emotion	      -

-auxiliary parameters

deductive

analysis

transferring parameters implies linking the general context to implementation,

macro to micro variables, and predicting interaction from isolated traits

vary individually

Latent processes are outcomes of interactions between project participants.  Elements of A and B are known beforehand and can be extrapolated from one project observed to a future one:

	Exchange -A					Exchange -B

inductive analysis

Content -A					Content -B

Interface -A 					Interface -B

Latent processes have higher transferability between projects than a management parameter or project context element.  Linking latent processes is more inductive because both are forms of interaction:

they reflect all isomorphic aspects of aid, whether political, organizational or individual, i.e. one interaction resembles another interaction more than the context of either one.

6.    Project parameters shaping latent processes and

the links to those EU Quality Standards that these

processes impinge upon

Example from a public infrastructure project

Cause              Effect ( Wirkung)

Parameter	   Latent Process	  Variable Quality Standards

task structuration		content 		2.3 Linkages with policy, programme and

interface  		       projects, supportive of ongoing work

local / foreign task	content

division		exchange		5.2 Complementarity with programmes /

knowledge output,		content        		      projects of other donors assessed

technology

budgeting,		exchange 		3.4 Assessment of institutional structures

inventories		interface 		      capacity and governance issues

performance		content		3.3 Conflicts between stakeholders

indicators		interface 		      identified and analysed

decisions		exchange		3.2 Stakeholder consultation and interests

meetings and		exchange 		      (expectations and concerns) analysed

agendas		interface		8.1 Management responsibilities build on

role conflict		exchange		     institutional arrangements and capacity

interface

evaluation		content

interface		15.4 Institutional strengthening and

official reporting,		content 		       capacity building, skills transferred

documentation		exchange

interface		8.3 Review, planning, budgeting fit with

language,		interface 		      local systems, respond to lessons

terminology		content    		     learned and changing circumstances

employment,		interface

remuneration			    		14.4 Operational plans reviewed and

accessory data,		exchange 		      lessons learned reflected

calculations		content   		5.3 Implementation strategies and further

non-essential aspects:	exchange 		      formulation work analysed

hours, transport, etc	interface

The most salient parameters are often some 20 out of a long list of possible parameters.  The salient ones reflect sectoral and organizational conditions but not individual participants.  The size of competitor organizations, the type of competition in the market segment and governance frequently decide which parameters are the most influential.  For this infrastructure project, the access to power grid data and to cost information played a role.  Other possible parameters are, for example, role clarity, formality, delegation, authority, accountability.

7. Possible influence of ‘Task Structuration’ on variable EU

Quality Standards, similar to other project parameters

Especially from economic sociology (most relevant only for this parameter)

| Quality Standard |  | horizontal: all expertise of one professional field finalised before next stage and expertise is used vertical: tasks divided into parallel applications, teams work in geographic or organizational separation |
| --- | --- | --- |
| 8.1 15.4 | Management responsibilities build on institutional arrangements and capacity | a - when stakeholders are linked with economic externalities, any project impact changes their relations: horizontal exposes biases, vertical exposes other biases b - formal institutions can realign with successive shifts in structuration, but the extent is uncertain c - informal institutions need to be probed and historical links can shift unpredictably d - capacity is often different for vertical or horizontal |
| 3.4 | Key stakeholders’ institutional structures, capacity and governance | a - ownership can depend on structuration b - when key stakeholders discover new issues, changes in structuration can allow to shape governance or create norms c - when key stakeholders are larger organizations, professional fields cut through or divide departments and networks underlying departments |
| 3.3 3.2 | Stakeholder interests and conflicts | a - interests are linked to economic externalities b - mutual recognition, trust, learning between stakeholders can evolve with structuration changes c - conflicts can change in nature when linked to socio-professional groups |
| 2.3 | Linkages and consistency with programmes, policy and projects | a - linkages evolve when stakeholder interests or conflicts change as indicated above, and in addition to this, structuration strengthens or weakens linkages b - task structuration can be used to avoid duplicating institutional structures and other linkages are then possible |
| 5.3 6.5 | Implementation strategies | some design work is possible only after the above influences have run their course, and additional interests and capacities appear; structuration allows to re-design because vertical separations can often be introduced at any point; local context is generally fluid and linkages contingent |
| 5.2 | Complementarities with planned programmes and other donors | a - in addition to linking tasks with related projects, complementarities can consist of small differences in structuration to encourage other forms of coordination b - when structuration affects stakeholder relations, larger differences with other projects can become necessary c - institutional structures assumed by other donors evolve |
| 6.1 | Objectives for policy or sector contribute to long term outcome | a - sector objectives often consist of structuration, thus the impact is contingent on monitoring the effectiveness of this structuration to maintain its effectiveness; trade or industrial associations’ influence in a sector often depends On creating rules and structuration can target this influence |

8.3 and 14.4 are influenced by all parameters

8.   Different analytical steps necessary for

Content

Formulation:    Context            Exchange                PCM                Quality

Interface

fixed		       Content

Management:               Context            Quality S.                Exchange

Interface

PCM,

variable Quality S.,

Project parameters

Evaluation:                     Context                           Implementation

Impact

Quality Standards

Monitoring:                     Context                         Implementation

Content

Exchange

Interface

PCM

9.      Three Levels of Data in Project Cycles

Key Question - which elements from one level can be combined with another

Example from a public infrastructure project

Typical Issues 	    Sources of data	    Project Premises

Context	markets, trade, 		newspapers,		Aid Dialogue: 		 		international			statistics,		institutions decide

relations, 			history books		efficiency, political

macroeconomics					regime, foreign

investment syndrome

Participants	interest negotiations,	observe and		Insiders’ hypotheses:

defining roles			participate in 	institutions are bound by

events,		invisible resistances,

reports		efficiency is also

normative

Community	direct stakeholders,		observe		Local folk theories:

traditional institutions,	adjacent		institutions are

social hierarchy affected,	developmental	accidental, government

relation to state		activities		and donors are far,

resources are merit

goods

The analytical orientation is INSIDE - OUT:

Combine these sources of data and account for all premises by defining

 Interface Process	 Exchange Process	 Content Process

and align parameters (contracts, people, time, information) to intensify project implementation.  Frequently comprises making participants shape PCM, regulations and demands from the donors, thereby increasing contextualisation, participation and unique elements.

The following analytical orientation is OUTSIDE - IN:

When is a combination of parameters transferable to another project ?

Allowing agencies to learn contextualisation, to enable participants and expand their needs of recording and documenting their work.

10.    Realistic Approximations:   First Analytical Step

Formulation - 	Only the context and the community is already known.

1. Step:  Predict the exchange process from the context

This is easier than the interface or content process, because the latter depend more on participants’ faculties (which the designer cannot predict).  The exchange process follows from a smaller number of possible global / local exchange patterns. The designer can use divers sources of information, from local newspapers to social psychology literature and history books.  The crucial question is - what happens in the passage from the global to the local sphere, does the knowledge become enabling or inhibiting in the eyes of the carrier ?  Frequently, it is useful to study the fate of related knowledge, or artefacts, designs, or money in exchanges of similar social groups.

Manager -	1. Step:  Pick the most influential parameter and test all 3 process

definitions

The ability to observe and describe project events in suitable terms decides whether the manager can define improvements.  During ongoing project work, all processes are constantly upheld by participants (as unintended outcomes). So the manager can repeat observations and parameter choice.  Better observation skills can also be brought in from outside.  When the influence of the parameter modification on the Quality Standards appears, this process definition is tested further with other parameters.  Thereby, the processes’ definitions are continuously improveable, as long as the interaction between participants allows to observe the processes.

Monitor -	1. Step: Seek indications for content and exchange processes which

can improve PCM

Content and exchange processes are the most important factors shaping the project evolution through the PCM stages.  As an important outsider, the monitor’s observation ability is limited. To go beyond accounting for results and efforts undertaken, monitoring must include assessing whether the mutual appreciation of professional bias and sociocultural ends indicate that the content process changes, and whether the use of know-how indicates that the exchange process changes.  Quality Standard 8.1 and objectives related to capacity building are frequently dependent on the exchange and content processes. There is no general recommendation possible on how or where to find such indications.

- Parameters and the generally decisive processes for aligning all

parameters’ form and combination to reinforce implementation

Frequent

Parameter	       forms	 	  Latent Process and Extent of Influence

task structuration	    horizontal	 content by exposing biases between the teams: extent rel.

-		         to HRM, sector or educational institutions.

vertical  	interface by reducing competition as labels shift: extent

rel. to larger social range but unit autonomy is possible.

local / foreign task	     parallel  	content by inviting differences in local/foreign images: rel.

division		          -		   to sectors because biases and ends have less scope.

intermittent	exchange by local / foreign attributes: extent rel. to

historical unit (Friedman), economic and trade patterns.

knowledge output,	     function      content by differences in sociocultural ends:  rel. to

technology	          -		  educational institutions, STS structures are institutionally

object	  shaped, thus objects do not fit other trajectories.

budgeting,	   aggregated 	 exchange by adding identity risks: extent rel. to social

inventories	          -     	    identities, whose interest is defined against outsiders.

specific	interface affected by categories (roles and project matter)

but ambiguities are reduced: extent individual.

performance	 discretionary  content by indirectly strengthening attribution: extent HRM

indicators	          -     	 modes or professional orgs seen as maintaining biases or ends.

public	interface ambiguity-fix: extent individuals clarifying roles.

decisions			     vertical	      exchange by permitting different local positioning to appear:

-			  extent rel. to stakeholders present, exchange formats do

nested		  not change but decision nodes make them more effective.

meetings and		     separate,   exchange via changes in subject/object relation assigning

agendas			       fixed		  items to people, in team: procedures adapt to social identity.

-	     interface by allowing ambiguity, only when roles and rhetoric

intermittent	  interact: extent project unit,	otherwise little dynamic.

role conflict	     passively 	exchange in endo-cases: extent social history, for know-how

tolerated	   deficits; in exo-cases weakly:  ext. rel. historical unit.

-       	interface endo-cases weakly: social history, inability to use;

acknowledged	   exo-cases:forces unit out of social history, expose ind. risks.

evaluation			   negotiated	content efforts to translate, group autonomy, encourages

-    	   change agents and leadership, supports aid history analysis.

fixed		interface project trails local politics, reduce confrontations.

official reporting,	   integrated	content by strengthening attribution, repetitive applications.

documentation	          -		exchange endo-cases:individual leaves group, isolated results.

separate	interface only weakly: reduces rhetoric scale, no recognition.

language,			      create		 interface efforts to translate far more relevant than their

terminology		  dictionary   -	   content, specific knowledge corpora created.

all vernacular	content by labelling tacitness and no need to define further.

employment,		  show all TOR	 Supports profiles, increases defensiveness, fosters explicit

remuneration		  	    -			   knowledge exchanges, endo case: increases individual failure.

hide terms	   Creates distance, role suspicion, implicit images guessing.

accessory data,		    extensive 	exchange exo-cases: shift alterity to other objects in social

calculations			    - 		   history, crucial; endo-cases: little influence on relations.

little		content by revealing ends: ext. rel. professions, expose bias.

non-essential aspects:	      group 		exchange exo-cases: social identity can blur focus; endo-

hours, transport, etc		    -			   cases: individuals pledge social identity, joint interest vague.

individual 	interface reduce/reinforce group identity: ext. rel. to HRM

modes and sector, facilitates agenda setting efforts.

„Project Cycle Management Guidelines“, volume 1 European Commission Aid Delivery Methods, march

2004, Brussels: EuropeAid Cooperation Office, p. 22.

One mayor reason for the new PCM was to include explicit criteria for institutional analysis.

„Whenever the Logframe needs to be revised the stakeholder analysis should also be re-

considered, as the landscape of stakeholders involved in a project evolves over time“ (Project Cycle

Management Guidelines, p. 66).

„Project Cycle Management Guidelines“, p. 57.

While Logframe use varies among donors, the habits of Logframe use described here are almost

uniform.  Few donors have commissioned studies to identify their specific in-house Logframe use,

which reflects a reluctance to investigate organisational behaviour.  Perhaps this reluctance also

helps to claim donor harmonization even where Logframe use is different.  See

Leeuw Frans 2002 “Assumptional Analysis, Logframe Analysis, and other Methods of

Deconstructing and Evaluating Program Logic”, Working Paper, Utrecht University.

Gasper Des 2000 „Evaluating the „logical framework approach” - towards learning-oriented

development evaluation”, Public Administration and Development, 20/1: 17-28.

Gasper Des 1997 ‘Logical Frameworks’: A Critical Assessment. Managerial Theory, Pluralistic

Practice, ISS Working Paper Series no. 264, p. 9–12.

Such doubts are necessarily part of the social process engaged.  Irrespective of the fact that even

the foremost experts cannot settle such an issue, for example, Appadurai assigning the rise of

chauvinistic Hindu nationalism in India to fears over cultural purity, whereas Friedman asserts that

not purity but the danger felt for individual identity as life form is at stake (Friedman Jonathan

2003 Globalization, the state and violence, Oxford: AltaMira, p. 24).

Uncertainty over local reasons and goals is in itself the strongest common denominator for even

diverse local experts and participants -- who is affiliated with foreign interests and who can

defend the community’s?  See also,

Appadurai Arjun 1996 Modernity at large: cultural dimensions of globalization, Minneapolis:

University of Minnesota Press.

Friedman Jonathan & Randeria Shalini 2004 Worlds on the move: globalization, migration, and

cultural security, London: I.B. Tauris.

„First, the project’s purpose is soften confused with its goal and therefore tends to be unrealistic,

given the time and resources dedicated.  Second, outputs are not always well specified and thus do

not provide a clear and logical link between activities and purposes“ (Poate et.al. 2000 „The

evaluability of democracy and human rights projects. A logframe-related assessment”, Sida

Studies in Evaluation, No. 00/3, Stockholm: Sida, p. xii).  The „Project Cycle Management

Guidelines“ also refer to the „mechanistic“ use of Logframes, op.cit.: 69.

Elaborate procedures to use Logframes and account for the differences in perspectives and

worldviews among stakeholders, such as in the German ZOPP, have been used for many years but

finally could not overcome the structurally induced tendencies of Logframe use (Gasper 1997,

op.cit.: 19-20).  The „Project Cycle Management Guidelines“ state that getting consensus on

priority problems and project objectives is problematic, but never qualify the assumption, op.cit.:

59.

„Generally speaking, stakeholders present good ideas on how to measure project success, but there

has not usually been any planning process whereby they share and come to an agreement on these

ideas.  This contributes to what may be termed a „smoke-screen“ problem whereby there is no

common and clear standard against which project performance can be monitored“ (Poate 2000,

op.cit.: xii).  Also Gasper 1997, op.cit.: 13, and Smith Peter 2000 „A Comment on the Limitations of

the Logical Framework Method, In Reply to Gasper and to Bell“, Public Administration and

Development, 20: 429-441.

Gasper 1997, op.cit.: 14.

Gasper 1997, op.cit.: 27.

„According to one ODA advisor, the logframe was more‚ a symbolic statement of aspirations than a

practical management tool….  TeamUp was only subject to criticism when, for example, senior

members of a powerful Indian bureaucracy were able to use it to derive‚ a less satisfactory design

than ODA might wish for“ (Mosse David 2005 Cultivating Development. An Ethnography of Aid

Policy and Practice, London: Pluto Press, p. 253).

Neither input nor output serve the needs of managers because the project is not linking these,

as a result, the activities become an intermediate measuring tool.  The management needs

effectively result in inefficient indicators.  See also  Biggs Stephen and Smith Sally 2003 „A

Paradox of Learning in Project Cycle Management and the Role of Organizational Change”, World

Development, 31/10: 1743-1757.

Habermas Jürgen 1998 On the Pragmatics of Communication, Cambridge: MIT, p. 248.

Habermas Jürgen 1981 Die Theorie des Kommunikativen Handelns, Frankfurt: Suhrkamp, p. 367.

Coleman Gilroy 1992 „Monitoring and Evaluation on Agricultural and Rural Development Projects:

Lessons and Learning”, Journal of International Development, 4/5: 497-510, p. 508.  The „Project

Cycle Management Guidelines“ also use the label „fetish“, op.cit.: 59.

Sabel Charles 1994 “Learning by Monitoring”, in Rodwin Lloyd and Schön Donald, Rethinking the

Development Experience: Essays Provoked by the Work of Albert O. Hirschman, Washington:

Brookings Institution.

Human Resources Management.

Alsop Ruth 1998 “Nests, Nodes and Niches: A System for Process Monitoring, Information

Exchange and Decision Making for Multiple Stakeholders”, World Development, 26/2: 249-260.

Mosse suggests (2005, op.cit.: 228) that participatory approaches are not possible in agriculture

because these require more time than the policy horizon of aid agencies allows.  His case study on

the IBRCP shows that UK consultants had to intervene constantly to allow adivasi casts to benefit

from this project.  A similar argument has been made for development management in general by

Bill Cooke, see Cooke 1996 “Participation, “process” and management: lessons for development in

the history of organisation development”, IDPM Human Resources in Development Group Working

Papers, No.7, and in a shortened form in Cooke 2003 “A new continuity with colonial

administration: participation in development management“, Third World Quarterly, 24/1: 47-61.

Strathern Marilyn 2000 Audit Cultures, London: Routledge.

Friedman Jonathan 1994 Cultural Identity & Global Process, London: SAGE.

Also important in democracy and human rights support, as well as NGO support, see Poate et al.

- Poate et al. suggest (2000, op.cit.: 77) that NGO support is a separate sector from

democracy and human rights.  The importance of vernacular language for health projects lies in the

cultural differences of health-related representations, whereas in NGO support, vernacular

language has more obvious political sensitivity.

Friedman Jonathan 1994, op.cit.

Human Resources Management.

Friedman Jonathan 2004, op.cit.: 74.

Science and Technology Studies.  See Mosse 2005 (op.cit.) for an application of STS to an

ethnology of the gap between policy and practice.

‘Trajectory’ is used in evolutionary economics, to describe technological sector dynamics.

According to Scott MacKenzie a technological trajectory is an institution which like any institution

is sustained not through any internal logic but because of the interests that develop in its

continuance and the belief that it will continue.

Alsop Ruth 1998, op.cit.

Strathern Marilyn 2000, op.cit.